## Tabelle1
| Requirement(s) | Satisfied (Yes/No/Partial) | Realization | Comment | Consumed time | Total time Estimation | Problems | Tested | Suggestions to expand requirements | Assigned by
FRs | E0, E1 | Partial | In assets/Scripts/Enemy.cs | armor and resistance missing, different types of enemy | 6h | - | - | partially |  | Jonas
| E2 | Yes | In assets/Scripts/WaveSpawner.cs and assets/Scripts/Wave.cs | including creating the first map and UI-Elements, spawnrate is adjustable | 10h | - | - | partially | Adjust the Spawnrate for each wave | Jonas
| E3 | Partially | In Playerstats.cs and Enemy.cs |  | 2h |  |  | partially |  | Jonas
| E4 | No | [7 empty] | Jonas
| E5 | Yes | In assets/Scripts/Enemy.cs and scene "musterscene" |  | 2h |  |  | partially |  | Jonas
| T0 | No
| T1 | Partially | In turret.cs |  | 0.5h
| T2 | No
| T3 | No
| T4 | No
| T5 | No
| T6 | No
| T7 | No
| S0 | No
| S1 | No
| Sys0 | Yes | In scene "Main Menu" and assets/Scripts/SceneSwitcher.cs |  | 1h | 1h |  | Yes, but no automated test | Change name from "Sx" to "Sysx" | Ben
| Sys1 | No | [6 empty] | Change name from "Sx" to "Sysx" | Ben
| Sys2 | Yes | In scene "musterscene" and assets/Scripts/PauseGame.cs |  | 1h | 0.75h |  | Yes, but no automated test | Change name from "Sx" to "Sysx" | Ben
| Sys3 | Partial | In scene "musterscene" and assets/Scripts/PauseGame.cs |  | 1h | 5h | Design question still open | Yes, but no automated test | Change name from "Sx" to "Sysx" | Ben
| Sys4 | Yes | In scene "musterscene" | Skipping game mode | - | - |  |  | Change name from "Sx" to "Sysx" | Ben
| Sys5 | Partial | In scene "musterscene" and assets | Towers missing |  |  |  |  | Change name from "Sx" to "Sysx" | Jonas
| Sys6 | No | [6 empty] | Change name from "Sx" to "Sysx" | Ben
NFRs | 2.3.1 User interface and human factors | Partial |  | On the fly progress
| 2.3.2 Documentation | Partial |  | On the fly progress
| 2.3.4 Performance characteristics | ? |  | Will be tested at the end
| 2.3.5 Error handling and extreme conditions | ?